## Dashboard
Hippocampus v1 — Implementation Tracker
Metric | Value | Phase | Name | Tasks | Done | Completion %
Total Tasks | 169 | 0 | Engineering Foundation | 15 | 0 | 0%
Done | 0 | 1 | Identity + Core Student Workspace | 11 | 0 | 0%
In Progress | 0 | 2 | Subjects + Topics + Learning Materials | 13 | 0 | 0%
Blocked | 0 | 3 | File Processing & Ingestion | 18 | 0 | 0%
Overall Completion | 0% | 4 | Knowledge Base + RAG Foundation | 14 | 0 | 0%
|  | 5 | AI Provider & Prompt Infrastructure | 14 | 0 | 0%
Execution Rule | Meaning | 6 | AI Learning Engine | 14 | 0 | 0%
Status = Done | Build + tests + Definition of Done satisfied; evidence recorded. | 7 | Study Missions | 14 | 0 | 0%
Ready for Review | Implementation complete; waiting for reviewer/gate confirmation. | 8 | Learning Evidence + Review System | 12 | 0 | 0%
Blocked | Cannot proceed because a documented dependency or decision is unresolved. | 9 | Visual & Multimodal Learning | 10 | 0 | 0%
Phase PASS | All Must tasks Done, required gate task Done, and acceptance evidence recorded. | 10 | Complete Student Learning Experience | 10 | 0 | 0%
|  | 11 | Security + Reliability Hardening | 12 | 0 | 0%
|  | 12 | Evaluation + Performance + Pilot Readiness | 12 | 0 | 0%

## Implementation Tracker
ID | Phase | Workstream | Implementation Task | Goal | What We Need to Build | How It Works | Dependencies | Tests / Validation | Expected Result | Definition of Done | Priority | Status | Owner | Evidence / Link | Notes / Blockers | Authority Docs
P0-01 | 0 | Repository | Create backend repository structure | Establish a clean Spring Boot codebase aligned with the modular-monolith architecture. | Create Maven Spring Boot project, Java 25 toolchain, base packages: identity, learning, progress, review, materials, rag, ai, shared, bootstrap. | Only bootstrap wiring may depend broadly; feature modules must start with explicit boundaries. | None | mvn test; application context starts; Java 25 verified. | Backend starts locally with no architecture violations. | Build passes, health endpoint responds, repository structure matches Doc 19. | Must | Not Started |  |  |  | 17,19,26
P0-02 | 0 | Repository | Create frontend repository structure | Establish React application baseline. | Create React 19 + TypeScript + Vite project with app, features, components, api, hooks, state, schemas, types, test folders. | App shell owns providers/router; feature folders own feature UI. | None | npm test/build/typecheck/lint. | Frontend loads base route without runtime/type errors. | Build/test/typecheck pass; folders match Doc 20. | Must | Not Started |  |  |  | 17,20,26
P0-03 | 0 | Backend | Configure Spring profiles | Separate local/test/pilot configuration safely. | Create application.yml plus local/test/pilot profiles; externalize secrets and resource limits. | Runtime selects profile; secrets are injected via environment. | Backend project | Profile-specific smoke tests; no secrets in Git. | App boots in local and test profiles with correct overrides. | Profiles documented and no secret values committed. | Must | Not Started |  |  |  | 17,19,22,23
P0-04 | 0 | Database | Provision local PostgreSQL + pgvector | Provide reproducible local relational/vector infrastructure. | Create Docker Compose PostgreSQL 18 with vector and pg_trgm extensions. | Developers start DB locally; Spring connects through env config. | Backend project | Container starts; SELECT extversion for vector; pg_trgm enabled. | Local DB is reproducible from one command. | Compose file works and extension tests pass. | Must | Not Started |  |  |  | 17,18,23
P0-05 | 0 | Database | Initialize Flyway | Make schema evolution version-controlled from day one. | Configure Flyway and create baseline migration for extension/bootstrap objects only. | App startup validates/applies migrations; Hibernate uses validate. | Local PostgreSQL | Empty DB migration test; second startup is idempotent. | Schema builds from zero consistently. | CI migration-from-zero test passes. | Must | Not Started |  |  |  | 17,18,25
P0-06 | 0 | Architecture | Add architecture enforcement tests | Prevent module drift early. | Configure ArchUnit rules for API→application→domain/ports and infrastructure isolation. | CI fails if forbidden dependencies appear. | Backend structure | Introduce deliberate violation test locally, then remove; CI green. | Forbidden layer dependencies are automatically detected. | Architecture tests run on every PR. | Must | Not Started |  |  |  | 19,25
P0-07 | 0 | Backend | Create error contract foundation | Standardize API failures before features expand. | Implement ProblemDetail/error-code mapper, correlation ID filter, common domain/application exception hierarchy. | Controllers throw typed errors; central handler maps stable code/message/correlationId. | Backend project | Controller test for validation, not-found, conflict, internal error. | Errors are consistent and do not leak internals. | Stable error JSON verified. | Must | Not Started |  |  |  | 19,22,24
P0-08 | 0 | Observability | Add Actuator and structured logging | Make foundation observable immediately. | Enable safe health endpoints, Micrometer baseline, JSON/structured log fields, correlation IDs. | Every request receives opaque correlation ID propagated to logs. | Backend project | Health test; log smoke test; sensitive-value grep. | Health works and logs contain no secrets. | Liveness/readiness and correlation verified. | Must | Not Started |  |  |  | 17,24
P0-09 | 0 | Frontend | Create application shell and routing | Provide consistent app frame without feature sprawl. | Implement router, auth-placeholder layout, compact navigation shell, route-level error boundary. | Feature routes render inside app shell. | Frontend project | Route smoke tests at desktop/mobile widths. | Core routes render and unknown routes fail gracefully. | Navigation shell works responsively. | Must | Not Started |  |  |  | 20
P0-10 | 0 | Frontend | Create centralized API client | Prevent ad hoc fetch usage. | Implement base URL, credentials, JSON/problem parsing, AbortSignal and multipart helpers. | All feature API modules depend on this client. | Frontend project | Unit tests for 2xx, 4xx ProblemDetail, network abort. | Errors normalize consistently. | No direct fetch calls outside approved client/streaming abstraction. | Must | Not Started |  |  |  | 20,22
P0-11 | 0 | Frontend | Create core UI states/components | Standardize basic UX. | Implement Button, Input, Textarea, Select, Card, Dialog/Drawer, Badge, Progress, Skeleton, EmptyState, ErrorState. | Features compose these without creating a huge UI library. | Frontend project | Component tests + keyboard/focus smoke tests. | Reusable states render consistently. | Core component suite passes accessibility smoke tests. | Must | Not Started |  |  |  | 20,25
P0-12 | 0 | CI/CD | Create GitHub Actions quality pipeline | Make quality gates automatic. | Add backend tests, frontend lint/typecheck/test, architecture tests, migration integration tests, secret/dependency scans, builds. | PR must pass deterministic checks before merge. | Repositories | Open sample PR; intentionally fail one check. | CI blocks broken code and reports failures clearly. | Required jobs green on main. | Must | Not Started |  |  |  | 23,25
P0-13 | 0 | Security | Add secret scanning and dependency monitoring | Prevent credential leaks and known vulnerable dependencies. | Configure Gitleaks and Dependabot/security alerts where available; add ignore process documentation. | Scans run on PR/schedule; findings are triaged. | CI pipeline | Synthetic fake-secret fixture in isolated test; dependency alert workflow review. | Secrets and vulnerable dependency signals are visible before release. | Security checks documented and active. | Must | Not Started |  |  |  | 22,24,25
P0-14 | 0 | Testing | Create Testcontainers foundation | Provide realistic integration tests. | Configure PostgreSQL 18 + pgvector Testcontainer base test support. | Integration tests create isolated DB and run Flyway. | Backend + Docker | Repository smoke test against container. | CI can test actual PostgreSQL behavior. | Reusable integration test base committed. | Must | Not Started |  |  |  | 17,25
P0-15 | 0 | Documentation | Create implementation tracker process | Make completion evidence mandatory. | Add tracker workflow, statuses, phase-gate rules, authority references, evidence links. | Task may only move to Done when DoD and tests pass. | Docs frozen | Review tracker with Phase 0 tasks. | Implementation work has a single progress source. | Tracker committed and used in PR workflow. | Must | Not Started |  |  |  | 26,27
P1-01 | 1 | Database | Create user schema | Persist internal user identity. | Create users table/entity/repository with UUID, email, display_name, status, timestamps. | Internal user ID is ownership root; provider/session details remain separate. | P0 Flyway | Migration/repository CRUD/unique-email tests. | Users persist and unique constraints hold. | Migration + entity mapping + repository tests pass. | Must | Not Started |  |  |  | 18
P1-02 | 1 | Security | Implement authentication flow | Allow a student to establish an authenticated session. | Implement chosen v1 login credential flow using Spring Security; map identity to users.id. | Successful authentication creates/uses server-side session. | User schema | Auth integration tests: valid/invalid/disabled user. | Authenticated user can enter app; invalid credentials reveal no sensitive details. | Auth tests pass and flow documented. | Must | Not Started |  |  |  | 22
P1-03 | 1 | Security | Configure Spring Session JDBC | Persist sessions server-side. | Enable Spring Session JDBC and required schema; configure idle timeout. | Browser stores only secure session cookie. | Authentication flow | Session persistence/expiry/restart tests. | Session survives app restart if DB remains; expired sessions fail. | Session tests pass. | Must | Not Started |  |  |  | 17,22
P1-04 | 1 | Security | Implement CSRF protection | Protect cookie-authenticated mutations. | Configure Spring Security CSRF and frontend token acquisition/submission. | GETs read; state-changing requests require valid CSRF token. | Auth/session | Missing-token rejection and valid-token success tests. | Cross-site forged state change is rejected. | CSRF tests pass. | Must | Not Started |  |  |  | 22,25
P1-05 | 1 | Security | Restrict CORS | Allow only approved origins. | Configure local and pilot frontend origins with credentials support. | Backend rejects credentialed requests from unapproved origins. | Profiles | CORS integration tests. | Approved frontend works; wildcard credentialed CORS absent. | CORS tests pass. | Must | Not Started |  |  |  | 22
P1-06 | 1 | Domain | Create current-user access abstraction | Remove client-controlled ownership identity. | Implement CurrentUser/AuthenticatedUser port resolved from Spring Security principal. | Application use cases obtain user ID server-side. | Authentication | Unit/integration tests; attempts to inject userId ignored/rejected. | Resource ownership always derives from session. | No use case accepts client userId as authority. | Must | Not Started |  |  |  | 19,22
P1-07 | 1 | Backend | Implement /me session endpoint | Give frontend safe session/user context. | Return minimal user profile/session state. | Frontend queries /me on authenticated shell bootstrap. | Current-user abstraction | API tests authenticated/unauthenticated. | Frontend can determine logged-in user without tokens. | Endpoint stable and privacy-minimal. | Should | Not Started |  |  |  | 20,22
P1-08 | 1 | Frontend | Implement login/session recovery UX | Handle auth lifecycle cleanly. | Create login screen, protected routes, session bootstrap, expired-session redirect, return-path handling. | TanStack Query tracks /me; no tokens in localStorage. | Auth API | RTL/Playwright login/logout/expiry tests. | User logs in/out; expired session returns safely to login. | Critical E2E auth journey passes. | Must | Not Started |  |  |  | 20,25
P1-09 | 1 | Frontend | Clear private state on logout | Prevent shared-device leakage. | Clear query cache, user-scoped Zustand, active streams and drafts on logout. | Logout response invalidates backend session then frontend state. | Frontend auth | Component/E2E shared-device test. | Next user cannot see previous user's cached data. | Logout privacy test passes. | Must | Not Started |  |  |  | 20,22
P1-10 | 1 | Security | Add ownership authorization test harness | Make IDOR checks reusable for every future resource. | Create test helpers with User A/User B and assertion patterns for 403/404/no data. | Every new user-owned API reuses harness. | Auth | Harness self-test. | Cross-user tests become cheap and mandatory. | Harness used by subsequent phases. | Must | Not Started |  |  |  | 22,25
P1-11 | 1 | Gate | Phase 1 end-to-end gate | Prove private student workspace exists. | Run auth, session, CSRF, CORS, ownership and frontend journey as one release gate. | All Phase 1 pieces operate together. | All P1 tasks | Playwright + backend security suite. | Student securely enters and exits private workspace. | All Phase 1 acceptance tests green; no cross-user leak. | Must | Not Started |  |  |  | 26
P2-01 | 2 | Database | Create subject/topic/subtopic schema | Persist learner organization. | Create subjects, topics, subtopics tables/entities/repos with ownership path and archive status. | Subject belongs to user; Topic belongs to Subject; one explicit Subtopic level. | P1 identity | Flyway, FK, uniqueness, ownership repository tests. | Organization persists with correct hierarchy. | Schema and CRUD tests pass. | Must | Not Started |  |  |  | 18
P2-02 | 2 | Backend | Implement Subject CRUD use cases/API | Allow user-owned subject management. | Create create/list/get/update/archive subject use cases and REST endpoints. | All queries derive authenticated owner. | Subject schema | API validation and User A/B authorization tests. | Student only sees own subjects. | CRUD and IDOR suite pass. | Must | Not Started |  |  |  | 19,22
P2-03 | 2 | Backend | Implement Topic/Subtopic CRUD use cases/API | Allow organization within subjects. | Create topic/subtopic create/list/update/archive APIs with parent ownership validation. | Topic cannot be attached to another user's subject. | Subject API | CRUD, invalid parent, archive tests. | Hierarchy remains ownership-safe. | API tests pass. | Must | Not Started |  |  |  | 18,19
P2-04 | 2 | Database | Create Material and MaterialVersion foundation | Persist upload lifecycle separately from learning topics. | Create materials/material_versions schema with storage key, statuses, active_version_id, hashes/metadata. | Material belongs to user; versions are immutable source revisions. | P1 + Flyway | FK/version uniqueness/status tests. | Materials can have versioned lifecycle. | Schema/repository tests pass. | Must | Not Started |  |  |  | 18
P2-05 | 2 | Storage | Implement object-storage port | Separate binary storage from DB. | Create BinaryObjectStore port + local filesystem/local S3-compatible implementation for development. | Backend stores opaque storage key; user filename is display metadata only. | Material schema | Contract tests: put/get/delete, traversal-safe keys. | Original file can be stored/retrieved locally without DB blob. | Storage contract tests pass. | Must | Not Started |  |  |  | 17,21,22
P2-06 | 2 | Backend | Implement upload initialization endpoint | Accept supported material and create processing placeholder. | Multipart endpoint validates basic limits/type, stores original, creates Material + v1 + initial state/job placeholder. | HTTP returns quickly; does not parse whole document. | Object store + material schema | Multipart API tests: valid, empty, unsupported, oversized synthetic. | Upload returns PROCESSING/UPLOADED metadata promptly. | API and storage tests pass. | Must | Not Started |  |  |  | 19,21
P2-07 | 2 | Backend | Implement material list/detail/delete | Let student manage uploaded resources. | Create list/detail/delete APIs including status and metadata. | Delete immediately removes future retrieval eligibility when later indexes exist. | Material foundation | Authorization, pagination, delete-state tests. | Student sees only own materials and can remove them. | CRUD + ownership tests pass. | Must | Not Started |  |  |  | 18,22
P2-08 | 2 | Database | Create MaterialTopicLink | Keep Material ≠ Topic while allowing mappings. | Create material_topic_links with origin/status/version/node optional references. | Mapping is many-to-many and validates same-user ownership. | Subject/topic + material | Cross-user mapping rejection, duplicate-active-link tests. | A material can support many topics and vice versa. | Schema/use-case tests pass. | Must | Not Started |  |  |  | 14,18
P2-09 | 2 | Frontend | Build Subjects and Topics UI | Make organization usable without feature overload. | Create subject list, subject detail, topic cards/forms, archive interactions. | Primary CTA from topic is future Study Mission, not tool selector. | Subject/topic APIs | RTL + Playwright CRUD journey. | Student organizes study areas cleanly. | Desktop/mobile CRUD flow passes. | Must | Not Started |  |  |  | 20
P2-10 | 2 | Frontend | Build Materials UI and upload transfer progress | Provide simple upload lifecycle. | Create materials list, file picker/drop zone, transfer progress, metadata and delete UI. | Transfer progress is distinct from backend processing progress. | Material APIs | Component/E2E upload tests. | Student can upload and see accepted file immediately. | Upload journey passes. | Must | Not Started |  |  |  | 20,21
P2-11 | 2 | Security | Harden upload intake baseline | Reject obvious malicious/invalid input before parsing. | Validate filename as metadata, MIME via Tika/content, size and supported types; safe generated storage keys. | Input cannot select paths or bypass type checks. | Upload API | Path traversal filename, disguised MIME, empty/corrupt/basic limit tests. | Unsafe intake is rejected safely. | Security fixture tests pass. | Must | Not Started |  |  |  | 21,22,25
P2-12 | 2 | Observability | Add material lifecycle telemetry | Make uploads diagnosable. | Log/metric material accepted/rejected/deleted and status changes using IDs only. | No source content or secrets in logs. | Material lifecycle | Inspect logs; privacy grep tests. | Operations can diagnose upload lifecycle. | Telemetry fields documented/tested. | Should | Not Started |  |  |  | 24
P2-13 | 2 | Gate | Phase 2 end-to-end gate | Prove private learning organization and upload lifecycle. | Run create subject/topic, upload file, link/delete, cross-user checks. | All components operate together. | All P2 tasks | Playwright + backend integration. | Student can organize private materials safely. | Phase gate green. | Must | Not Started |  |  |  | 26
P3-01 | 3 | Database | Create ProcessingJob schema | Persist durable pipeline state. | Create processing_jobs table/entity with type,status,priority,progress,attempts,locks,next_attempt,heartbeat/error fields. | Worker state survives restarts. | P2 materials | Migration/constraint tests. | Jobs can be claimed/retried durably. | Schema tests pass. | Must | Not Started |  |  |  | 18,21
P3-02 | 3 | Processing | Implement atomic job claiming | Prevent duplicate worker execution. | Implement PostgreSQL FOR UPDATE SKIP LOCKED claim transaction. | Worker marks RUNNING/lock fields then commits before work. | ProcessingJob | Two-worker concurrency integration test. | Only one worker claims a job. | Concurrency test passes. | Must | Not Started |  |  |  | 21,25
P3-03 | 3 | Processing | Implement processing dispatcher and stage handlers | Make pipeline explicit. | Create dispatcher plus VALIDATE/EXTRACT/STRUCTURE/VISUAL/NORMALIZE/CHUNK handlers. | Each stage is independent, observable and retryable. | Job claiming | Unit tests per dispatcher route. | Jobs execute correct handler and next stage. | Handler contract tests pass. | Must | Not Started |  |  |  | 21
P3-04 | 3 | Parsing | Implement PDF metadata/native text extraction | Read native PDFs in batches. | Use Tika/PDFBox to detect page count, metadata, extract ordered page text without whole-file string. | Persist bounded batch output. | Object storage + jobs | Native PDF fixture, 600-page synthetic/fixture memory test. | Native PDFs become page/text blocks with progress. | Fixture output matches expected. | Must | Not Started |  |  |  | 21,25
P3-05 | 3 | Database | Create DocumentNode/TextBlock schema | Persist source structure before chunking. | Create document_nodes/text_blocks tables/entities/repos with source order/page/extraction quality. | Blocks retain hierarchy and provenance. | Extraction | Migration/repository tests. | Normalized source structure is queryable. | Tests pass. | Must | Not Started |  |  |  | 18,21
P3-06 | 3 | Parsing | Classify pages by extraction type | Drive OCR decisions safely. | Classify NATIVE_TEXT/MIXED/IMAGE_ONLY/UNREADABLE using native extraction signals. | Only pages needing OCR go to OCR port. | PDF extraction | Mixed/scanned fixture classification tests. | Pages route correctly. | Classification tests pass. | Must | Not Started |  |  |  | 21
P3-07 | 3 | OCR | Create OCR port and initial implementation | Support scanned pages without coupling pipeline. | Define OcrPort/OcrResult and select practical initial implementation for local/pilot; persist method/quality. | OCR uncertainty remains metadata. | Page classification | Strong/poor/no-text fixture tests. | Scanned pages yield text or explicit limitation. | Adapter tests pass; engine documented. | Must | Not Started |  |  |  | 21,27
P3-08 | 3 | Parsing | Implement structure detection heuristics | Recover chapters/sections cheaply before AI. | Use bookmarks/TOC/font/layout/numbering/repeated patterns to create DocumentNodes. | Native signals first; AI not required for obvious structure. | Text blocks | Golden structure fixtures. | Known headings/sections detected with source order. | Fixture hierarchy matches expected tolerance. | Must | Not Started |  |  |  | 21
P3-09 | 3 | AI/Ingestion | Implement bounded AI-assisted structure fallback | Use AI only for ambiguous hierarchy. | Create typed structure-detection AI task for unresolved segments with strict structured output/versioning. | Only ambiguous sampled content is sent; output labeled AI_ASSISTED. | P5 AI provider normally later; create interface/stub now and enable after P5 | Mock contract tests now; live enablement deferred. | Pipeline can defer ambiguous structure without blocking deterministic extraction. | Stub boundary complete; no premature provider coupling. | Should | Not Started |  |  |  | 10,21
P3-10 | 3 | Visuals | Extract embedded/source visuals | Preserve anatomy/medical figures as first-class assets. | Extract images per page, store binary in object store, persist visual metadata/content hash. | Original image bytes retained with page/hierarchy. | PDF extraction + object store | Mixed PDF fixture expected visual count/page/hash. | Visuals survive extraction and retry without duplicates. | Visual fixture tests pass. | Must | Not Started |  |  |  | 18,21
P3-11 | 3 | Visuals | Associate captions and nearby text | Preserve visual context for later RAG. | Detect caption proximity/figure labels and create associations to blocks/nodes. | Uncertain association remains limited rather than fabricated. | Visual extraction + TextBlocks | Figure/caption golden fixtures. | Correct caption/nearby text attached. | Association tests pass. | Must | Not Started |  |  |  | 21
P3-12 | 3 | Tables | Implement safe table text handling | Keep common medical tables semantically useful. | Detect basic table-like layouts; preserve row/column text when reliable; fallback to visual/limited text otherwise. | Never invent cell relations when uncertain. | Extraction | Simple/complex/failure table fixtures. | Reliable tables searchable; uncertain tables marked limited. | Tests pass. | Should | Not Started |  |  |  | 21
P3-13 | 3 | Normalization | Normalize extraction safely | Remove noise without damaging medical notation. | Handle repeated headers/footers, line wraps/hyphenation conservatively; preserve Na+, Ca2+, β1, C5-T1 etc. | Normalization keeps original provenance. | TextBlocks | Golden medical-symbol tests. | Searchable text improves without term corruption. | Normalization regression suite passes. | Must | Not Started |  |  |  | 21
P3-14 | 3 | Chunking | Implement hierarchy-aware chunker | Create retrieval units from coherent source sections. | Chunk ordered blocks by semantic/document boundaries, token budget and conservative overlap; store heading path/page range/version. | Chunks are not topics. | Normalized blocks | Golden chunk fixtures; max-token and boundary tests. | Chunks are coherent, traceable and bounded. | Chunking tests pass. | Must | Not Started |  |  |  | 13,18,21
P3-15 | 3 | Processing | Implement progress/heartbeat/retry | Make long processing recoverable. | Update page/chunk progress and last heartbeat; classify transient/fatal/partial failures; bounded retries/backoff. | Restart resumes from durable intermediate state. | All handlers | Simulated timeout/provider/storage failures; restart test. | Jobs recover without duplicating output. | Recovery suite passes. | Must | Not Started |  |  |  | 21,24,25
P3-16 | 3 | Processing | Implement material READY/PARTIALLY_READY/FAILED derivation | Expose meaningful capability state. | Derive overall material/version state from required stage results and limitations. | READY only after required source structure/chunks/index prerequisites; partial preserves limitations. | Pipeline state | State matrix tests. | Frontend status accurately represents usable capability. | All matrix cases pass. | Must | Not Started |  |  |  | 21
P3-17 | 3 | Frontend | Build processing status and structure tree UI | Make ingestion transparent to students. | Show user-friendly stage text, progress, partial failures, collapsible detected hierarchy; poll with backoff. | Never show raw pgvector/worker jargon. | Processing APIs | RTL + E2E processing states incl partial/failure. | Student understands when material is usable and limitations. | UX tests pass. | Must | Not Started |  |  |  | 20,21
P3-18 | 3 | Gate | Phase 3 large-material gate | Prove 600+ page ingestion architecture works. | Run end-to-end large mixed PDF through extract/structure/visual/chunk/restart path. | Resource use bounded; no duplicate outputs. | All P3 | Large fixture, restart, memory/progress validation. | Large textbook reaches pre-index structured state reliably. | Gate evidence recorded. | Must | Not Started |  |  |  | 21,25,26
P4-01 | 4 | Database | Create IndexGeneration/ChunkEmbedding schema | Version embedding indexes explicitly. | Create index_generations and chunk_embeddings with provider/model/dimension/chunking version/status and uniqueness. | Generations never mix silently. | P3 chunks | Migration/uniqueness/dimension metadata tests. | Embeddings are generation-scoped and rebuildable. | Tests pass. | Must | Not Started |  |  |  | 18
P4-02 | 4 | RAG | Implement embedding port | Decouple retrieval indexing from provider. | Define EmbeddingPort and batch request/result contracts. | Provider/model implementation selected by configuration/evaluation. | Index schema | Fake adapter tests. | Chunk indexing is provider-independent. | Port tests pass. | Must | Not Started |  |  |  | 13,17
P4-03 | 4 | RAG | Implement initial embedding adapter | Produce v1 embeddings using approved candidate/provider. | Implement selected Gemini embedding adapter initially; capture model/dimension/usage. | No provider types escape adapter. | P5 AI/provider secrets may be reused; can implement direct adapter here | Contract/live smoke test with tiny quota. | Embeddings persist correctly. | Adapter and dimension tests pass. | Must | Not Started |  |  |  | 17
P4-04 | 4 | RAG | Implement batched embedding jobs | Index chunks efficiently and idempotently. | Create EMBED processing stage batching active chunks and upserting unique chunk+generation. | Transient failures retry without duplicate vectors. | Embedding port + jobs | Partial batch failure/retry tests. | All eligible chunks get one embedding per generation. | Idempotency tests pass. | Must | Not Started |  |  |  | 21
P4-05 | 4 | RAG | Implement lexical search repository | Support exact medical terms. | Build PostgreSQL FTS + pg_trgm search over active authorized chunks. | Metadata ownership/version filters applied in SQL. | Chunks | Queries for C5-T1, β1, CN VII etc. | Exact terms retrieve expected evidence. | Golden lexical tests pass. | Must | Not Started |  |  |  | 13,17
P4-06 | 4 | RAG | Implement vector search repository | Support semantic retrieval. | Implement pgvector similarity query constrained by allowed user/material/version scope. | Authorization filters occur before ranking. | Embeddings | User A/B similarity isolation test. | Semantically relevant chunks returned only from allowed scope. | Zero-leakage test passes. | Must | Not Started |  |  |  | 13,22
P4-07 | 4 | RAG | Implement hybrid candidate merge | Combine lexical and semantic strengths. | Merge/dedupe candidates using configurable scoring/rank fusion strategy. | No LLM needed for base retrieval. | Lexical + vector repos | Golden cases: exact, semantic, mixed. | Hybrid improves or matches expected retrieval. | Offline metrics recorded. | Must | Not Started |  |  |  | 13
P4-08 | 4 | RAG | Implement retrieval scope builder | Derive authorized search scope from task/topic/material links. | Build RetrievalScope from authenticated user, topic, active material versions/nodes and grounding mode. | Client cannot widen scope. | MaterialTopicLink + auth | Cross-user and inactive-version tests. | Every retrieval is scoped centrally. | Scope tests pass. | Must | Not Started |  |  |  | 13,22
P4-09 | 4 | RAG | Implement EvidencePackage builder | Return bounded, source-traceable context. | Create chunks, visuals, SourceReferences, quality/limitations and diagnostics payload. | Prompt layer receives normalized evidence, not SQL rows. | Hybrid retrieval | Unit/integration package tests. | EvidencePackage has valid sources and quality. | Source resolution tests pass. | Must | Not Started |  |  |  | 13,19
P4-10 | 4 | RAG | Implement source reference resolver | Make citations stable and authorized. | Create SourceReference records/resolution to page/node/chunk/visual and learner-facing labels. | Reference ID alone never bypasses authorization. | Evidence package | Forgery/cross-user/inactive tests. | Valid references open correct source. | Security tests pass. | Must | Not Started |  |  |  | 18,22
P4-11 | 4 | RAG | Create developer retrieval inspector | Let team inspect RAG before AI. | Protected local/admin diagnostic endpoint/tool shows query, candidate IDs/scores/headings/quality without exposing private text broadly. | Used only for development/authorized diagnostics. | RAG services | Manual/golden retrieval review. | RAG can be debugged independently of LLM. | Inspector available locally and access-controlled. | Should | Not Started |  |  |  | 24,26
P4-12 | 4 | Testing | Create Golden Retrieval Dataset v1 | Establish measurable retrieval quality baseline. | Create versioned queries with expected/acceptable sections/chunks and irrelevant negatives. | Use authorized synthetic/public fixtures. | RAG complete | Calculate Recall@K/Precision@K/MRR as appropriate. | Baseline quality known before AI phase. | Dataset committed; thresholds recorded. | Must | Not Started |  |  |  | 15,25
P4-13 | 4 | Security | Run RAG isolation release suite | Prove zero cross-user leakage. | Execute semantic-identical User A/B corpora, inactive/deleted material and forged scope tests. | Scope filtering must happen before ranking. | RAG complete | Automated security suite. | 0 unauthorized chunks ever returned. | Gate passes. | Must | Not Started |  |  |  | 22,25
P4-14 | 4 | Gate | Phase 4 retrieval gate | Prove source-grounded knowledge layer works without AI. | Run representative queries across anatomy/physiology exact/semantic/visual contexts and inspect EvidencePackages. | No generative model involved. | All P4 | Golden metrics + source resolution. | Hippocampus can reliably find correct authorized evidence. | Gate evidence recorded. | Must | Not Started |  |  |  | 26
P5-01 | 5 | AI | Define canonical AiTask contracts | Standardize AI tasks before providers. | Create typed AiTaskRequest/ValidatedAiResult and task enums/contracts for explanation, question, evaluation, connection, application, repair. | Canonical contract contains grounding/evidence/output schema. | P4 EvidencePackage | Serialization/unit tests. | All AI use cases speak one internal language. | Contracts stable and tested. | Must | Not Started |  |  |  | 10,12,19
P5-02 | 5 | AI | Implement PromptTemplateRegistry | Centralize versioned prompts. | Create registry for system + task templates with prompt ID/version and authority hierarchy. | Feature code cannot embed arbitrary production prompts. | AI contracts | Registry lookup/version tests. | Prompts are traceable and centrally managed. | No production prompt strings outside registry. | Must | Not Started |  |  |  | 12
P5-03 | 5 | AI | Implement PromptContextBuilder | Control tokens and untrusted boundaries. | Build minimal learner/activity/evidence context with explicit SOURCE_CONTEXT and STUDENT_RESPONSE delimiters and output budget. | Only task-relevant context is included. | Prompt registry + RAG | Snapshot/token-budget/prompt-injection fixture tests. | Prompts stay bounded and preserve instruction hierarchy. | Tests pass. | Must | Not Started |  |  |  | 12,22
P5-04 | 5 | AI | Implement ProviderRouter | Select provider centrally. | Create routing policy using task support, evaluation status, availability, quota/rate state, cost/latency config. | Learning/domain code never picks Gemini/Ollama. | AI contracts | Unit route matrix tests. | Correct route/fallback selected deterministically. | Routing tests pass. | Must | Not Started |  |  |  | 10,19
P5-05 | 5 | AI | Implement GeminiProviderAdapter | Connect Gemini server-side. | Use Spring AI Google GenAI integration; map canonical request, multimodal input where approved, structured outputs/errors/usage. | Gemini SDK types remain internal. | Provider router + secrets | Mock/contract + tiny live smoke test. | Gemini executes supported typed tasks. | Contract tests pass. | Must | Not Started |  |  |  | 17,19
P5-06 | 5 | AI | Implement OllamaCloudProviderAdapter | Connect remote Ollama API. | Use server-side HTTPS bearer auth and map canonical request/stream/errors. | No local Ollama assumption; provider-specific details stay internal. | Provider router + secrets | Mock HTTP/contract + tiny live smoke. | Ollama API executes supported typed tasks. | Contract tests pass. | Must | Not Started |  |  |  | 10,17,19
P5-07 | 5 | AI | Implement AI Request Manager | Bound concurrency and provider pressure. | Add per-provider concurrency gates, queue, timeouts, Retry-After/backoff, cancellation and circuit-breaker-like state. | Interactive tasks get higher priority than background AI. | Provider adapters | Concurrency/rate-limit/timeout tests. | Provider overload degrades predictably without flooding. | Tests pass. | Must | Not Started |  |  |  | 10,19,24
P5-08 | 5 | AI | Implement output schema validation | Keep provider output untrusted. | Parse structured output, validate enums/business constraints and required fields before returning ValidatedAiResult. | Invalid output cannot mutate learning state. | AI contracts | Malformed/missing/extra-field tests. | Only valid typed results cross AI boundary. | Validation suite passes. | Must | Not Started |  |  |  | 10,12,22
P5-09 | 5 | AI | Implement source-reference validation | Prevent fabricated citations. | Validate provider-returned source IDs are subset of supplied EvidencePackage and still authorized/active. | Forgery causes AI_GROUNDING_FAILURE or repair path. | Output validation + RAG | Fabricated/cross-user/inactive reference tests. | AI cannot invent accepted citations. | Security tests pass. | Must | Not Started |  |  |  | 22,25
P5-10 | 5 | AI | Implement bounded repair/retry | Recover format errors without loops. | Allow one/few configured structured-output repair attempts using same task/evidence/policy. | Do not retry safety/authorization failures as availability errors. | Validation | Repair success/failure tests. | Malformed provider output either safely repairs or fails transparently. | Bounded behavior verified. | Should | Not Started |  |  |  | 12,19
P5-11 | 5 | AI | Implement fallback orchestration | Preserve contract across providers. | On eligible provider availability failure, route same canonical task/evidence/grounding/schema to approved fallback. | Fallback cannot broaden context or weaken policy. | Router/adapters | Primary timeout/rate-limit/fallback tests. | Fallback works invisibly when contract-compatible. | Tests pass. | Must | Not Started |  |  |  | 10,22
P5-12 | 5 | Observability | Persist AI request/usage diagnostics | Measure quality/cost without content leakage. | Write ai_request_records/provider_usage_records with provider/model/task/prompt/tokens/latency/status/fallback. | Do not persist full prompts by default. | AI execution | DB/ privacy tests. | Operations can compare providers safely. | Telemetry verified. | Must | Not Started |  |  |  | 18,24
P5-13 | 5 | Testing | Create provider contract and prompt regression suite | Make AI integration stable. | Shared tests run against fake provider adapters; small scheduled live smoke set; prompt snapshots/golden schema cases. | PR CI avoids unnecessary quota. | All AI infra | CI/scheduled suite. | Provider changes do not silently break contracts. | Suites documented and green. | Must | Not Started |  |  |  | 25
P5-14 | 5 | Gate | Phase 5 AI infrastructure gate | Prove provider abstraction works independently of Learning Engine. | Execute same supported task via Gemini and Ollama; simulate primary failure and verify fallback/validation/telemetry. | RAG evidence remains identical. | All P5 | Contract + live smoke + fallback. | Provider can change without domain rewrite. | Gate evidence recorded. | Must | Not Started |  |  |  | 26
P6-01 | 6 | Domain | Define LearningState model | Represent only evidence needed for pedagogical decisions. | Create immutable domain view of mission state, evidence dimensions, source capability, time context and history. | No provider DTOs or UI state inside. | P1-P5 domain foundations | Pure unit tests. | Learning Engine receives deterministic input. | Model stable and provider-free. | Must | Not Started |  |  |  | 11,19
P6-02 | 6 | Domain | Define NextLearningAction model | Make engine outputs explicit. | Create typed actions: UNDERSTAND, RETRIEVE, CONNECT, APPLY, FEEDBACK/REFLECT/COMPLETE as approved with objective/difficulty/rationale/AI requirement. | Application layer interprets action. | LearningState | Unit serialization/equality tests. | No raw prompt text returned by engine. | Action model tested. | Must | Not Started |  |  |  | 11,19
P6-03 | 6 | Domain | Implement mission state machine policy | Protect valid progression lifecycle. | Implement planned/active/paused/completed/stopped transitions and validation. | Completion does not imply mastery. | Learning models | All valid/invalid transition unit tests. | Illegal transitions rejected deterministically. | State suite passes. | Must | Not Started |  |  |  | 11,18
P6-04 | 6 | Domain | Implement understand→retrieve policy | Move from explanation to active recall appropriately. | Define conditions for explanation then retrieval, respecting time/source capability and existing evidence. | Engine chooses action, AI only generates content later. | LearningState | Table-driven policy tests. | Weak/insufficient knowledge gets appropriate understanding/retrieval. | Cases pass. | Must | Not Started |  |  |  | 03,11
P6-05 | 6 | Domain | Implement connection policy | Require relational learning when appropriate. | Select CONNECT activities after basic understanding/retrieval when concept relationships matter. | Uses evidence not learning-style labels. | Evidence state | Scenario tests. | Connections appear at appropriate stage. | Policy tests pass. | Must | Not Started |  |  |  | 03,11
P6-06 | 6 | Domain | Implement application/scenario policy | Introduce practical medical application with scaffolding. | Choose APPLY when prerequisites are adequate; reduce difficulty or return to UNDERSTAND/RETRIEVE after weak performance. | Early students get educational scenarios, not clinical autonomy. | Evidence + objectives | Weak/strong application cases. | Appropriate application practice selected. | Policy suite passes. | Must | Not Started |  |  |  | 03,11
P6-07 | 6 | Domain | Implement time-aware mission policy | Fit learning sequence to available study time. | Use available_time and activity estimates to select bounded next actions/complete gracefully. | Timer does not equal mastery. | Mission context | 5/15/30-minute cases. | Mission remains coherent within time limit. | Tests pass. | Should | Not Started |  |  |  | 06,11
P6-08 | 6 | Domain | Implement scaffolding policy | Respond to difficulty without giving answers immediately. | Define retry → hint → simpler explanation/prerequisite → reattempt behavior. | Scaffolding is deterministic; wording may use AI. | Attempt history | Table-driven incorrect/partial cases. | Student receives progressively useful support. | Tests pass. | Must | Not Started |  |  |  | 03,11
P6-09 | 6 | Domain | Implement anti-repetition policy | Avoid mechanically repeating same question/activity. | Track recent activity/concept/template history and exclude unnecessary repeats while allowing deliberate spaced review. | No random repetition by provider. | History | Repeat-history unit tests. | Learning variety remains purposeful. | Tests pass. | Should | Not Started |  |  |  | 11
P6-10 | 6 | Domain | Implement source-capability policy | Never request unsupported activity types. | Use material capabilities/quality to avoid visual/source-strict tasks when unavailable or poor. | RAG/ingestion limitations feed engine. | Material capability | No-visual/limited-OCR/no-evidence cases. | Engine picks safe alternative or signals limitation. | Tests pass. | Must | Not Started |  |  |  | 11,21
P6-11 | 6 | Domain | Implement AI/RAG failure policy | Define pedagogical fallback when dependencies fail. | Map RAG LIMITED/INSUFFICIENT/FAILED and AI unavailable to reuse/source-only/retry/pause actions where appropriate. | Failure is explicit, never hidden as empty context. | RAG/AI result types | Failure matrix tests. | Mission degrades safely. | Tests pass. | Must | Not Started |  |  |  | 11,19
P6-12 | 6 | Testing | Create Learning Engine scenario suite | Prove pedagogy deterministically. | Build table-driven scenarios across evidence dimensions, time, misconceptions, source quality and history. | No live AI needed. | Engine policies | Hundreds of deterministic cases where practical. | Changes reveal pedagogical regressions. | Suite green and versioned. | Must | Not Started |  |  |  | 11,25
P6-13 | 6 | Architecture | Verify Learning Engine provider independence | Prevent AI authority drift. | ArchUnit rules block learning.domain dependencies on ai.infrastructure, Spring MVC/JPA/provider SDKs. | Engine may depend only on domain/ports/value types. | Architecture tests | Intentional violation check. | Learning Engine remains pure/testable. | CI rule active. | Must | Not Started |  |  |  | 19,25
P6-14 | 6 | Gate | Phase 6 Learning Engine gate | Prove Hippocampus can decide next action without LLM. | Feed representative student states and review expected actions/rationales. | No provider calls occur. | All P6 | Deterministic scenario suite. | Pedagogical sequencing is application-owned. | Gate evidence recorded. | Must | Not Started |  |  |  | 26
P7-01 | 7 | Database | Create StudyMission/LearningObjective/LearningActivity schema | Persist complete mission plan and current activity. | Implement tables/entities/repos and mission_materials/source links as Doc 18. | Mission freezes material versions. | P2-P6 | Migration/FK/version tests. | Mission can be resumed reproducibly. | Schema tests pass. | Must | Not Started |  |  |  | 18
P7-02 | 7 | Database | Create StudentAttempt schema | Keep immutable attempt history. | Persist attempt_number, response payload/text, evaluation status/artifact references. | Retries create new rows, never overwrite prior attempt. | Activities | Uniqueness/ordering tests. | Attempt history is traceable. | Tests pass. | Must | Not Started |  |  |  | 18
P7-03 | 7 | Application | Implement StartStudyMissionUseCase | Create bounded mission from topic, time and sources. | Validate ownership/readiness, freeze allowed material versions, derive objectives/initial state and first LearningEngine action. | RAG/AI called only if first action needs content. | Mission schema + engine | Use-case tests with ready/partial/no-source states. | Starting a mission yields first valid activity or clear limitation. | Tests pass. | Must | Not Started |  |  |  | 19
P7-04 | 7 | Application | Implement activity materialization | Turn NextLearningAction into concrete activity. | For deterministic actions create directly; for AI tasks retrieve EvidencePackage, execute typed task, validate, persist artifact/activity/source refs. | Engine decides kind; AI creates bounded content. | RAG + AI + mission | Integration tests by activity type. | Activity content is grounded and typed. | Tests pass. | Must | Not Started |  |  |  | 11,19
P7-05 | 7 | Application | Implement SubmitActivityResponseUseCase | Process student answer safely. | Persist/prepare attempt, evaluate deterministically or via AI, validate result, generate evidence event later, ask engine for next action, persist state in short transactions. | No DB transaction held across long provider call. | Activities + AI | Correct/partial/invalid/timeout/stale-state tests. | Answer leads to validated feedback and next action without duplicate state. | Tests pass. | Must | Not Started |  |  |  | 19
P7-06 | 7 | Application | Implement pause/resume/stop mission | Preserve continuity. | Add use cases and endpoints maintaining current activity/time/material versions. | Resume does not regenerate completed setup unnecessarily. | Mission state | State transition + restart tests. | Student can leave and return safely. | Tests pass. | Must | Not Started |  |  |  | 06,18
P7-07 | 7 | AI | Implement explanation task end-to-end | Support Understand activity. | Use EvidencePackage + objective + learner context → structured explanation/key points/source refs. | Supplemental knowledge classified explicitly. | AI infra + RAG | Golden explanation cases. | Explanation is source-grounded and learner-appropriate. | Tests/eval pass. | Must | Not Started |  |  |  | 07,12,15
P7-08 | 7 | AI | Implement retrieval-question task end-to-end | Support active retrieval activity. | Generate structured short-answer/MCQ/identification question with expected evidence, no answer leakage. | Backend controls activity type/difficulty. | AI infra | Question quality/golden cases. | Question tests target intended concept and sources. | Eval pass. | Must | Not Started |  |  |  | 03,07
P7-09 | 7 | AI | Implement response-evaluation task end-to-end | Provide formative feedback without false scoring. | Evaluate student response against expected evidence, return correctness dimensions/missing reasoning/misconception candidate/feedback contract. | Learning Engine/progress later interprets; AI doesn't set mastery. | AI infra | Correct/partial/alternative/wrong reasoning tests. | Evaluation is nuanced and structured. | Golden eval pass. | Must | Not Started |  |  |  | 11,15
P7-10 | 7 | AI | Implement concept-connection task | Generate bounded relationship activity. | Create connection explanation/question linking relevant concepts using evidence. | Engine decides when connection is needed. | AI infra | Golden connection cases. | Connections are medically relevant and source-grounded. | Eval pass. | Must | Not Started |  |  |  | 03,11
P7-11 | 7 | AI | Implement application-scenario task | Generate practical scaffolded medical scenario. | Create age-appropriate scenario focused on target concept with expected reasoning and safety/educational framing. | Not patient-specific advice. | AI infra | Scenario plausibility/difficulty/support tests. | Student can apply foundational knowledge meaningfully. | Eval pass. | Must | Not Started |  |  |  | 03,07,15
P7-12 | 7 | Frontend | Build Study Mission route and ActivityRenderer | Create core product experience. | Implement /missions/:id, typed union renderer for explanation/retrieval/connection/application/feedback/reflection, source panel and actions. | Frontend renders backend contract; never parses raw provider semantics. | Mission APIs | RTL for each activity + route E2E. | One coherent guided flow replaces feature menu. | Tests pass. | Must | Not Started |  |  |  | 20
P7-13 | 7 | Frontend | Implement mission submit/resume/conflict UX | Make mission reliable in real browser use. | Build useStudyMission hook, submit states, stale 409 refetch, pause/resume, timer display and source drawer. | Critical state changes wait for backend confirmation. | Mission APIs | Two-tab conflict E2E; refresh/resume tests. | Mission survives refresh and rejects double submission. | Tests pass. | Must | Not Started |  |  |  | 20
P7-14 | 7 | Gate | Phase 7 First Hippocampus gate | Prove full source-grounded Study Mission. | From topic + processed material: start mission → understand → retrieve → connect → apply → feedback → complete/pause. | Sources visible and provider abstracted. | All P7 | Critical Playwright E2E + source validation + AI golden checks. | M3 First Hippocampus works end-to-end. | Milestone evidence recorded. | Must | Not Started |  |  |  | 26
P8-01 | 8 | Database | Create EvidenceEvent/LearningEvidence schema | Persist traceable longitudinal learning evidence. | Implement evidence_events and learning_evidence summary tables by user/topic/concept/dimension/state. | Summary is recomputable from events. | P7 attempts | Migration/FK tests. | Evidence has event provenance. | Tests pass. | Must | Not Started |  |  |  | 18
P8-02 | 8 | Domain | Implement EvidenceProjector | Convert validated attempts to broad evidence states. | Deterministically aggregate events into STRONG/DEVELOPING/WEAK/INSUFFICIENT per dimension using approved rules. | No LLM sets final state. | Evidence schema | Table-driven projection tests. | Same events always yield same evidence. | Suite passes. | Must | Not Started |  |  |  | 11,18
P8-03 | 8 | Application | Integrate attempt→evidence transaction | Make validated activity affect future learning. | After validated evaluation, create EvidenceEvent and update projection in short transaction with mission state. | Invalid AI evaluation produces no evidence. | Submit use case + projector | Rollback/invalid-eval tests. | Evidence updates only from legitimate activity. | Tests pass. | Must | Not Started |  |  |  | 18,19
P8-04 | 8 | Database | Create misconception_evidence/reflection_evidence | Track weak conceptual patterns without permanent labels. | Implement schemas and links to supporting events/mission. | Single ambiguous response defaults POSSIBLE. | Evidence events | Promotion/resolution FK tests. | Misconceptions remain traceable/contextual. | Tests pass. | Must | Not Started |  |  |  | 18
P8-05 | 8 | Domain | Implement misconception policy | Promote/resolve misconception based on repeated evidence. | Define POSSIBLE→ACTIVE→RESOLVED logic and evidence thresholds/rationale codes. | AI may suggest candidate description, app owns status. | Evidence projector | Repeated-error/corrective cases. | No permanent label from one mistake. | Tests pass. | Must | Not Started |  |  |  | 11,18
P8-06 | 8 | Database | Create ReviewRecord and evidence links | Persist explainable review queue. | Implement review_records/review_evidence_links and optional mission linkage. | Review reason always traceable to evidence. | Evidence | Migration/query tests. | Due review items have evidence basis. | Tests pass. | Must | Not Started |  |  |  | 18
P8-07 | 8 | Domain | Implement ReviewPolicy | Determine what/why/when to revisit. | Use LearningEvidence + events + review history + time rules to create/update eligible_at/priority/reason. | No LLM chooses date. | Review schema | Fixed-clock policy tests. | Weak/decaying evidence creates appropriate review. | Tests pass. | Must | Not Started |  |  |  | 03,11,18
P8-08 | 8 | Application | Implement review queue/use cases | Expose due reviews and start review mission. | List available reviews by priority/reason; start a normal StudyMission linked to review record; complete updates evidence/review state. | Review uses same engine and source grounding. | Review policy + missions | Use-case/integration tests. | Review becomes part of learning loop, not separate quiz tool. | Tests pass. | Must | Not Started |  |  |  | 06,19
P8-09 | 8 | Frontend | Build Review route | Show what to revisit and why. | Display topic/concept, reason, priority/availability and CTA to start review mission. | Frontend never calculates schedule. | Review API | RTL/E2E due/no-due/completed. | Student understands reason for review. | Tests pass. | Must | Not Started |  |  |  | 20
P8-10 | 8 | Frontend | Build Progress evidence UI | Show multidimensional evidence without fake percentages. | Render Retrieval/Understanding/Connection/Application/Review Retention as broad states with recent context. | No mastery percentage unless future evidence supports it. | Progress API | Component/accessibility tests. | Progress is clear and non-misleading. | Tests pass. | Must | Not Started |  |  |  | 20
P8-11 | 8 | Testing | Create longitudinal learning regression scenarios | Prove previous evidence affects future missions. | Simulate mission attempts → evidence → review → later mission and assert engine action changes. | Use fixed clock and fake AI. | All P8 | End-to-end domain/integration scenarios. | Hippocampus adapts across sessions. | Suite green. | Must | Not Started |  |  |  | 25
P8-12 | 8 | Gate | Phase 8 Adaptive Hippocampus gate | Prove longitudinal loop. | Complete weak application attempt, observe evidence/review, run corrective review, verify later LearningEngine context/action changes. | All evidence traceable. | All P8 | Integrated scenario + UI E2E. | M4 Adaptive Hippocampus works. | Milestone evidence recorded. | Must | Not Started |  |  |  | 26
P9-01 | 9 | RAG | Add visual-aware retrieval | Allow source images to participate in EvidencePackage. | Retrieve linked VisualAssets using chunk/node/caption/nearby-text relevance and task need. | Text grounding still controls source scope. | P3 visuals + P4 RAG | Golden anatomy visual queries. | Relevant source figure accompanies evidence. | Visual retrieval tests pass. | Must | Not Started |  |  |  | 13,14
P9-02 | 9 | AI | Enable validated multimodal provider route | Use image understanding only where evaluation proves capability. | Add visual task support matrix to ProviderRouter; pass approved source image + bounded context to capable model. | Fallback only to provider supporting same multimodal contract. | P5 providers | Provider capability/unsupported fallback tests. | Visual task routes safely. | Tests pass. | Must | Not Started |  |  |  | 10,15
P9-03 | 9 | AI | Implement visual activity task contract | Generate/assess image-based learning activity. | Create typed visual-identification/interpretation request/result with source visual reference and expected concept. | Original image remains authoritative asset. | Visual RAG + multimodal provider | Golden anatomy/image cases. | Activity refers to actual source visual without fabricated labels. | Eval pass. | Must | Not Started |  |  |  | 07,12
P9-04 | 9 | Frontend | Build medical image viewer | Make source visuals usable for study. | Add zoom, pan, accessible lightbox/drawer, caption/source controls, responsive behavior. | No AI-generated replacement needed for source display. | Visual assets | Keyboard/touch/accessibility tests. | Student can inspect figures on desktop/mobile. | Tests pass. | Must | Not Started |  |  |  | 20
P9-05 | 9 | Frontend | Build VisualActivity component | Integrate visuals into Study Missions. | Render original source visual, prompt, response controls, feedback and citation. | Activity remains within mission flow, not separate tool. | Visual task API | RTL/E2E visual mission. | Image becomes active learning evidence. | Tests pass. | Must | Not Started |  |  |  | 20
P9-06 | 9 | Progress | Add VISUAL_IDENTIFICATION evidence dimension path | Track visual task performance appropriately. | Generate EvidenceEvents for validated visual activities and project dimension separately. | No visual-learner profiling. | Visual activity + evidence | Projection tests. | Visual evidence influences relevant future activity. | Tests pass. | Should | Not Started |  |  |  | 18
P9-07 | 9 | Ingestion | Handle visual-unavailable/limited capability | Prevent invalid visual activities. | Expose material_version capability metadata for visuals and failed extraction; engine respects it. | P3 states + P6 source policy | No-visual/failed-image cases. | Mission avoids visual task when source cannot support it. | Tests pass. | Must | 21 | Not Started
P9-08 | 9 | Testing | Create anatomy visual golden fixture set | Establish reliable multimodal validation. | Use licensed/synthetic anatomy diagrams with known source labels/relationships and expected retrieval/task outputs. | No real patient data. | Visual pipeline | Retrieval + AI + frontend visual tests. | Visual quality is measurable. | Fixtures committed and passing. | Must | Not Started |  |  |  | 25
P9-09 | 9 | Security | Test visual/source authorization | Prevent image leakage. | Attempt direct visual/source-reference access across users and expired signed URLs if used. | Authorization rechecked on every source access. | Visual endpoints | IDOR/signed URL tests. | 0 cross-user image access. | Tests pass. | Must | Not Started |  |  |  | 22,25
P9-10 | 9 | Gate | Phase 9 multimodal gate | Prove anatomy-style visual learning end-to-end. | Upload mixed PDF → extract image → retrieve visual → Study Mission identification → feedback/evidence. | All P9 | Full E2E and golden evaluation. | Visuals function as learning evidence, not decoration. | Gate evidence recorded. | Must | 26 | Not Started
P10-01 | 10 | Frontend | Complete Home dashboard | Answer what should I study now. | Implement continue mission, due reviews, recent topics/materials, quick start with compact hierarchy. | Avoid analytics overload. | P7-P8 APIs | E2E empty/active/review states. | Home leads student into next useful action. | Tests pass. | Must | Not Started |  |  |  | 20
P10-02 | 10 | Frontend | Complete Topic workspace | Unify material/evidence/mission entry. | Show topic, relevant material sections, recent evidence, review state, Start/Resume Mission. | No feature-tool menu. | P2/P7/P8 | Component/E2E. | Topic screen is clear learning launch point. | Tests pass. | Must | Not Started |  |  |  | 20
P10-03 | 10 | Frontend | Complete Material detail/source browser | Let student inspect detected structure and source limitations. | Add hierarchy tree, processing capabilities, page/source opening, topic mapping/selection. | Large hierarchy lazy-expands. | P3/P4 | Large tree performance + E2E. | Student can understand what material was processed. | Tests pass. | Must | Not Started |  |  |  | 20
P10-04 | 10 | Frontend | Complete mission completion summary | Close loop without fake mastery. | Show practiced objectives, broad evidence, weak areas, review expectation and next actions. | Completion is not mastery. | P8 | Component/content tests. | Student gets meaningful recap. | Tests pass. | Must | Not Started |  |  |  | 20
P10-05 | 10 | Frontend | Implement responsive/tablet/mobile polish | Ensure med-student usability beyond desktop. | Reflow nav/source panel, readable widths, touch targets, image viewer and forms at 320px+. | No page-level horizontal overflow. | All UI | Viewport matrix Playwright tests. | Core flows usable on laptop/tablet/mobile. | Tests pass. | Must | Not Started |  |  |  | 20
P10-06 | 10 | Accessibility | Run WCAG 2.2 AA core-flow remediation | Make core experience keyboard/screen-reader usable. | Fix focus, labels, contrast, live streaming announcements, dialog/drawer behavior, image controls. | Streaming must not announce every token. | All frontend | Automated axe-like checks + manual keyboard/screen-reader checklist. | Core journeys are accessibility-aligned. | Critical issues resolved. | Must | Not Started |  |  |  | 20,25
P10-07 | 10 | Frontend | Implement cold-start/connectivity UX | Handle free backend reality gracefully. | Detect initial backend delay/network loss; show Connecting; safe GET retries; preserve unsent draft locally where appropriate. | Do not auto-retry non-idempotent submissions without protection. | P23 deployment | Render cold-start simulation/E2E. | Free-tier sleep doesn't look like data loss. | Tests pass. | Must | Not Started |  |  |  | 20,23
P10-08 | 10 | Frontend | Standardize error/empty/loading states | Finish coherent product behavior. | Map stable backend error codes to actionable messages for material, AI, retrieval, conflicts, auth. | Unknown errors show correlation ID. | Backend error catalog | Component/E2E state matrix. | Failures are understandable and recoverable. | Tests pass. | Must | Not Started |  |  |  | 19,20,24
P10-09 | 10 | Performance | Frontend performance pass | Keep core experience responsive. | Route code-splitting, lazy PDF/image viewer, avoid over-fetching, virtualize large structure trees where needed. | Measure realistic devices. | Complete UI | Build analysis + performance smoke tests. | No obvious large-document UI freeze. | Performance notes recorded. | Should | Not Started |  |  |  | 20
P10-10 | 10 | Gate | Phase 10 complete UX gate | Prove full user journey feels like one product. | Login → home → subject/topic → material → mission → review/progress on desktop/mobile. | All P10 | Full Playwright journey/accessibility review. | Hippocampus feels coherent, not a feature collection. | Gate evidence recorded. | Must | 26 | Not Started
P11-01 | 11 | Security | Run full SAST baseline | Detect code-level security issues. | Run chosen CodeQL/FindSecBugs/Semgrep combination on backend/frontend and triage findings. | False positives documented narrowly. | Code complete | Security report review. | No unresolved exploitable Critical findings. | Report attached. | Must | Not Started |  |  |  | 25
P11-02 | 11 | Security | Run SCA/dependency audit | Detect vulnerable Maven/npm dependencies. | Run Dependabot/OWASP dependency checks/npm audit supplemental review; patch or document findings. | Versions follow Doc 17 policy. | Dependencies | Report + upgrade regression. | No release-blocking dependency vulnerabilities. | Gate satisfied. | Must | Not Started |  |  |  | 25
P11-03 | 11 | Security | Run secret exposure audit | Prove keys are absent from repo/build/logs. | Run Gitleaks/GitHub scanning and inspect frontend build artifacts/log samples. | Any exposed key is revoked/rotated. | Build artifacts | Synthetic pattern and real scan. | No active secrets exposed. | Scan passes. | Must | Not Started |  |  |  | 22,25
P11-04 | 11 | Security | Run container image scan | Check backend runtime/base image. | Use Trivy or approved scanner; review OS/JRE/dependency findings and Docker config. | Run non-root where practical. | Docker image | Scan report + runtime user check. | No release-blocking image vulnerability. | Report attached. | Must | Not Started |  |  |  | 25
P11-05 | 11 | Security | Run DAST/API security suite | Challenge deployed controlled environment. | Use OWASP ZAP/manual API cases for auth, headers, methods, common web weaknesses. | Never run destructive test against real pilot data. | Test environment | DAST report. | No critical web/API vulnerability. | Findings resolved/accepted. | Must | Not Started |  |  |  | 25
P11-06 | 11 | Security | Run explicit IDOR/CSRF/CORS/XSS suite | Validate core web trust boundaries. | Execute User A/B resources, missing CSRF, bad origins, malicious topic/source/AI markdown payloads. | 0 cross-user access; scripts inert. | Complete app | Automated security integration/E2E. | Trust boundaries hold. | Tests pass. | Must | Not Started |  |  |  | 22,25
P11-07 | 11 | Security | Run upload/parser abuse suite | Protect ingestion availability. | Test disguised MIME, traversal filename, corrupt/encrypted/extreme pages, oversized image, resource amplification and stage timeouts. | One file cannot crash whole service. | P3 pipeline | Security fixtures/load. | Unsafe files fail safely. | Tests pass. | Must | Not Started |  |  |  | 21,25
P11-08 | 11 | Security | Run prompt injection/RAG forgery suite | Prove AI cannot escalate authority. | Inject source/student instructions, request system prompt/cross-user data, forged source refs. | Scope/grounding/validation remain unchanged. | AI/RAG | Golden adversarial cases. | No authority or data-scope escalation. | Tests pass. | Must | Not Started |  |  |  | 22,25
P11-09 | 11 | Reliability | Run provider outage/fallback drills | Validate graceful AI degradation. | Simulate Gemini down, Ollama down, both down, auth failure, rate limit, timeout. | Student work preserved; fallback only when compatible. | AI layer | Resilience integration tests. | System remains consistent and transparent. | Tests pass. | Must | Not Started |  |  |  | 24,25
P11-10 | 11 | Reliability | Run Neon/R2/backend restart drills | Validate persistence/recovery. | Simulate DB unavailable, R2 timeout, Render restart mid-job/mission. | No fake persistence; jobs resume; mission state remains consistent. | Infrastructure abstractions | Controlled failure tests. | Recovery matches runbooks. | Tests pass. | Must | Not Started |  |  |  | 24,25
P11-11 | 11 | Operations | Verify kill switches and incident runbooks | Ensure team can contain failures. | Test config disable for providers/uploads/OCR/large processing; verify provider key rotation and incident steps. | Core data remains available where safe. | Feature flags/config | Manual drill checklist. | High-risk capability can be disabled without code rewrite. | Runbook evidence recorded. | Should | Not Started |  |  |  | 22,24
P11-12 | 11 | Gate | Phase 11 security/reliability gate | Decide whether release is safe enough for pilot. | Aggregate all security scans, adversarial tests and resilience results; classify remaining findings. | Critical exploitable issues block. | All P11 | Formal checklist review. | No release-blocking security/reliability issue. | Gate signed/recorded. | Must | Not Started |  |  |  | 25,26
P12-01 | 12 | Evaluation | Run final Golden RAG evaluation | Prove retrieval quality on representative medical sources. | Execute versioned dataset across exact, semantic, mixed, visual queries; capture Recall@K/Precision@K/MRR and failure cases. | Use final active index generation. | P4/P9 | Automated evaluation run. | Metrics meet documented pilot threshold; failures understood. | Report/version stored. | Must | Not Started |  |  |  | 15,25
P12-02 | 12 | Evaluation | Run final AI task evaluation | Validate Gemini/Ollama task quality and routing. | Evaluate explanation, questions, response evaluation, connections, scenarios, visual tasks where supported using shared rubrics. | Record provider/model/prompt versions. | P5-P9 | Golden AI evaluation. | Routing choices have evidence and core tasks pass quality gates. | Report stored. | Must | Not Started |  |  |  | 15,25
P12-03 | 12 | Evaluation | Review medical correctness sample | Add qualified human review for high-impact task samples. | Review representative generated explanations/evaluations/scenarios for correctness, overreach and clarity. | Student feedback does not replace correctness review. | AI evaluation | Reviewer rubric. | No systematic dangerous medical error. | Findings addressed. | Must | Not Started |  |  |  | 15,25
P12-04 | 12 | Performance | Benchmark ingestion capacity | Measure real large-file resource use. | Process native/scanned/mixed 600+ page materials; record time, peak memory, chunks, storage growth, retries. | Use pilot-like limits. | P3 | Benchmark suite. | Configured limits are evidence-based. | Results documented. | Must | Not Started |  |  |  | 21,25
P12-05 | 12 | Performance | Run 10-user load profile | Establish baseline pilot behavior. | Simulate realistic mix of browsing, missions, AI, one/few uploads. | Not 10 infinite simultaneous generations. | Complete system | Load test. | Latency/queues/resources acceptable. | Metrics stored. | Must | Not Started |  |  |  | 25
P12-06 | 12 | Performance | Run 20-user load profile | Validate scaling trend. | Repeat realistic mixed workload and observe DB/provider/backend pressure. | Compare to 10-user baseline. | 10-user test | Load test. | No unstable queue/storage growth. | Metrics stored. | Must | Not Started |  |  |  | 25
P12-07 | 12 | Performance | Run 40-user load profile | Validate target pilot capacity. | Simulate approximately 40 invited-user behavior with bounded uploads/AI and concurrent missions. | Respect provider free-tier test budget; mocks may supplement live quota tests. | 20-user test | Load simulation + targeted live provider checks. | System remains usable or explicit quotas/limits are adjusted before pilot. | Capacity decision recorded. | Must | Not Started |  |  |  | 23,25,26
P12-08 | 12 | Infrastructure | Validate free-tier capacity and quotas | Ensure PILOT-FREE limits are realistic. | Measure Neon DB growth, R2 objects/storage, Render behavior/cold starts, Gemini/Ollama usage and projected exhaustion. | Set warning/critical thresholds. | Load/ingestion data | Capacity spreadsheet/report. | Pilot quotas prevent surprise exhaustion. | Thresholds configured. | Must | Not Started |  |  |  | 23,24
P12-09 | 12 | Operations | Verify backup and restore | Prove recoverability. | Create pg_dump/approved backup, restore to isolated DB, run Flyway/schema/integrity smoke tests; verify source metadata consistency. | Never overwrite pilot during test. | P23 ops | Restore checklist. | Backup is actually usable. | Restore evidence recorded. | Must | Not Started |  |  |  | 24,25
P12-10 | 12 | E2E | Run full release-candidate journey | Validate complete student flow after all hardening. | Login → organize → upload/process → study mission → visual task → evidence → review → progress → logout; include error recovery. | Use RC deployment. | All phases | Playwright/manual exploratory/accessibility. | Core product works end-to-end. | RC E2E green. | Must | Not Started |  |  |  | 25
P12-11 | 12 | Release | Complete release gate checklist | Make pilot decision explicit. | Review all Document 25 blocking criteria, vulnerabilities, known limitations, privacy disclosure, runbooks and capacity. | No unresolved blocker can be hand-waved. | All P12 | Formal checklist. | Hippocampus v1.0.0-RC approved or rejected with reasons. | Decision recorded. | Must | Not Started |  |  |  | 25,26
P12-12 | 12 | Pilot | Prepare controlled pilot configuration | Deploy only after gate passes. | Configure invited users, quotas, monitoring thresholds, support/contact path, privacy/educational disclaimer and feedback/evaluation plan. | PILOT-FREE remains controlled, non-commercial validation. | Release gate | Pilot smoke test. | Environment is ready for real med-student use within known limits. | M5 evidence complete. | Must | Not Started |  |  |  | 22,23,26

## Phase Gates
Phase | Phase Name | Primary Goal | Milestone | Total Tasks | Done | In Progress | Blocked | Completion % | Gate Result | Gate Evidence / Notes
0 | Engineering Foundation | Reproducible Java/Spring + React foundation with DB, CI, security and architecture tests. | M0 — Engineering Skeleton | 15 | 0 | 0 | 0 | 0% | Not Evaluated
1 | Identity + Core Student Workspace | Secure private student identity, session lifecycle and ownership boundary. | — | 11 | 0 | 0 | 0 | 0% | Not Evaluated
2 | Subjects + Topics + Learning Materials | Students can organize subjects/topics and privately upload/manage learning materials. | — | 13 | 0 | 0 | 0 | 0% | Not Evaluated
3 | File Processing & Ingestion | Large/mixed medical files become structured, traceable chunks/visuals through durable processing. | M1 — Material Workspace | 18 | 0 | 0 | 0 | 0% | Not Evaluated
4 | Knowledge Base + RAG Foundation | Authorized hybrid retrieval returns inspectable EvidencePackages before any generative AI. | — | 14 | 0 | 0 | 0 | 0% | Not Evaluated
5 | AI Provider & Prompt Infrastructure | Gemini and Ollama execute the same typed tasks behind provider-independent routing and validation. | M2 — Grounded Intelligence | 14 | 0 | 0 | 0 | 0% | Not Evaluated
6 | AI Learning Engine | Deterministic Learning Engine selects appropriate next pedagogical action without LLM authority. | — | 14 | 0 | 0 | 0 | 0% | Not Evaluated
7 | Study Missions | Student completes a full source-grounded Study Mission from explanation through application/feedback. | M3 — First Hippocampus | 14 | 0 | 0 | 0 | 0% | Not Evaluated
8 | Learning Evidence + Review System | Attempts become traceable evidence and drive future review/learning across sessions. | M4 — Adaptive Hippocampus | 12 | 0 | 0 | 0 | 0% | Not Evaluated
9 | Visual & Multimodal Learning | Source visuals actively participate in retrieval, Study Missions and evidence. | — | 10 | 0 | 0 | 0 | 0% | Not Evaluated
10 | Complete Student Learning Experience | All core capabilities form one accessible, responsive, guided student experience. | — | 10 | 0 | 0 | 0 | 0% | Not Evaluated
11 | Security + Reliability Hardening | System withstands security/adversarial/dependency/provider/infrastructure failure tests. | — | 12 | 0 | 0 | 0 | 0% | Not Evaluated
12 | Evaluation + Performance + Pilot Readiness | RAG/AI/ingestion/load/backup/E2E evidence supports controlled ~40-student pilot decision. | M5 — Pilot Candidate | 12 | 0 | 0 | 0 | 0% | Not Evaluated

## Lists
Status | Priority | Phase | Gate Result
Not Started | Must | 0 | Not Evaluated
In Progress | Should | 1 | PASS
Blocked | Could | 2 | FAIL
Ready for Review |  | 3
Done |  | 4
5
6
7
8
9
10
11
12